## Slide 1: Risk Mitigation
By
Yulhendri

## Slide 2: Risk
Risk management - the art and science of identifying, analyzing, and responding to risk factors throughout the life of a project and in the best interest of its objectives.
Project risk – any possible event that can negatively affect the viability of a project

## Slide 3: Risk Vs Amount at Stake
Phase 1 Conceive (C)
Phase 2 Develop (D)
Phase 3 Execute (E)
Phase 4 Finish (F)
Time
$ Value
Increasing Risk
Total Project Life Cycle
Amount at stake
Plan
Produce
Opportunity and risk
Period of highest risk impact
Combined risk impact

## Slide 4: Process of Risk Management
What is likely to happen?
What can be done?
What are the warning signs?
What are the likely outcomes?
Project Risk = (Probability of Event)(Consequences of Event)

## Slide 5: Four Stages of Risk Management
Risk identification
Analysis of probability and consequences
Risk mitigation strategies
Control and documentation

## Slide 6: Risk Clusters
Financial
Technical
Contractual/Legal
Commercial
Execution
Common Types
Absenteeism
Resignation
Staff pulled away
Time overruns
Skills unavailable
Ineffective Training
Specs incomplete
Change orders

## Slide 7: Risk Factor Identification
Brainstorming meetings
Expert opinion
Past history
Multiple (or team based) assessments

## Slide 8: Risk Impact Matrix
Consequences
Likelihood
High
Low
Low
High

## Slide 9: Project Risk Scoring
Identify factors and assess the probability (Pf ) and consequences (Cf) of failure
Calculate overall probability & consequence
Calculate overall risk factor

## Slide 10: Risk Mitigation Strategies
Accept
Minimize
Share
Transfer
Contingency Reserves
  Task contingency
  Managerial contingency
Mentoring
Cross training

## Slide 11: Control & Documentation
Help managers classify and codify risks, responses, and outcomes
Change management report system answers
What?
Who?
When?
Why?
How?

## Slide 12: Project Risk Analysis & Management
Extends risk management over project’s life cycle
Key Features of PRAM
Risk management follows a life cycle
Risk management strategy changes over the project life cycle
Synthesized, coherent approach

## Slide 13: Nine Phases of Risk Assessment
Define
Focus
Identify
Structure
Clarify ownership of risks
Estimate
Evaluate
Plan
Manage