## Slide 1: Chapter 9
Project Management
(Project Evaluation & Review Technique – PERT)

## Slide 2: Lecture Outline
Probabilistic Activity Times
Project Crashing and Time-Cost Trade-off

## Slide 3: Probabilistic Time Estimates
Beta distribution
  probability distribution traditionally used in CPM/PERT
a = optimistic estimate
m = most likely time estimate
b = pessimistic time estimate
where
Mean (expected time): t =
a + 4m + b
6
Variance: 2 =
2
b - a
6

## Slide 4: Examples of Beta Distributions
P(time)
P(time)
P(time)
Time
a
m
t
b
a
m
t
b
m = t
Time
Time
b
a

## Slide 5: Project with Probabilistic Time Estimates
Finish
2
3,6,9
3
1,3,5
1
6,8,10
5
2,3,4
6
3,4,5
4
2,4,12
7
2,2,2
8
3,7,11
9
2,4,6
10
1,4,7
11
1,10,13
Equipment installation
System development
Position recruiting
Equipment testing and modification
Manual testing
Job Training
Orientation
System training
System testing
Final debugging
System changeover
Start

## Slide 6: Activity Time Estimates
1 6 8 10 8 0.44
2 3 6 9 6 1.00
3 1 3 5 3 0.44
4 2 4 12 5 2.78
5 2 3 4 3 0.11
6 3 4 5 4 0.11
7 2 2 2 2 0.00
8 3 7 11 7 1.78
9 2 4 6 4 0.44
10 1 4 7 4 1.00
11 1 10 13 9 4.00
TIME ESTIMATES (WKS) MEAN TIME VARIANCE
ACTIVITY a m b t б2

## Slide 7: Activity Early, Late Times & Slack
ACTIVITY t б ES EF LS LF S
1 8 0.44 0 8 1 9 1
2 6 1.00 0 6 0 6 0
3 3 0.44 0 3 2 5 2
4 5 2.78 8 13 16 21 8
5 3 0.11 6 9 6 9 0
6 4 0.11 3 7 5 9 2
7 2 0.00 3 5 14 16 11
8 7 1.78 9 16 9 16 0
9 4 0.44 9 13 12 16 3
10 4 1.00 13 17 21 25 8
11 9 4.00 16 25 16 25 0

## Slide 8: Earliest, Latest, and Slack
1
0
8
8
1
9
3
0
3
3
2
5
4
8
13
5
16
21
6
3
7
4
5
9
7
3
5
2
14
16
9
9
13
4
12
16
10
13
17
1
0
3
2
0
6
6
0
6
5
6
9
3
6
9
8
9
16
7
9
16
11
16
25
9
16
25
Critical Path 2-5-8-11
Finish
Start

## Slide 9: Total Project Variance
2 = б22 + б52 + б82 + б112
= 1.00 + 0.11 + 1.78 + 4.00
= 6.89 weeks

## Slide 10: Probabilistic Network Analysis
Determine probability that project is completed within specified time
where
 = tp = project mean time
 = project standard deviation
x = proposed project time
Z = number of standard deviations that x is from the mean
Z =
x - 


## Slide 11: Normal Distribution of Project Time
 = tp
Time
x
Z
Probability

## Slide 12: Southern Textile
What is probability that project is completed within 30 weeks?
 2 = 6.89 weeks
 = 6.89
 = 2.62 weeks
Z =
=
= 1.91
x - 

30 - 25
2.62
From Table A.1, (appendix A) a Z score of 1.91 corresponds to a probability of 0.4719. Thus P(30) = 0.4719 + 0.5000 = 0.9719
 = 25
Time (weeks)
x = 30
P(x  30 weeks)

## Slide 13: Southern Textile
What is probability that project is completed within 22 weeks?
 2 = 6.89 weeks
 = 6.89
 = 2.62 weeks
Z =
=
= -1.14
x - 

22 - 25
2.62
From Table A.1, (appendix A) a Z score of 1.14 corresponds to a probability of 0.3729. Thus P(22) = 0.5000 - 0.3729 = 0.1271
 = 25
Time (weeks)
x = 22
P(x  22 weeks)
= 0.1271
0.3729

## Slide 14: Project Crashing
Crashing
  reducing project time by expending additional resources
Crash time
  an amount of time an activity is reduced
Crash cost
  cost of reducing activity time
Goal
  reduce project duration at minimum cost

## Slide 15: Project Network – Building a House
1
12
2
8
4
12
3
4
5
4
6
4
7
4

## Slide 16: Normal Time and Cost vs. Crash Time and Cost
$7,000 –
$6,000 –
$5,000 –
$4,000 –
$3,000 –
$2,000 –
$1,000 –
–
| | | | | | |
0 2 4 6 8 10 12 14 Weeks
Normal activity
Normal time
Normal cost
Crash time
Crashed activity
Crash cost
Slope = crash cost per week

## Slide 17: Project Crashing
TOTAL
NORMAL CRASH ALLOWABLE CRASH
TIME TIME NORMAL CRASH CRASH TIME COST PER
ACTIVITY (WEEKS) (WEEKS) COST COST (WEEKS) WEEK
1 12 7 $3,000 $5,000 5 $400
2 8 5 2,000 3,500 3 500
3 4 3 4,000 7,000 1 3,000
4 12 9 50,000 71,000 3 7,000
5 4 1 500 1,100 3 200
6 4 1 500 1,100 3 200
7 4 3 15,000 22,000 1 7,000
$75,000 $110,700

## Slide 18
Project Duration:
36 weeks
1
12
2
8
3
4
5
4
6
4
7
4
$400
$500
$3000
$7000
$200
$200
$7000
12
4
FROM …
1
7
2
8
3
4
5
4
6
4
7
4
$400
$500
$3000
$7000
$200
$200
$7000
12
4
Project Duration:
31 weeks
Additional Cost:
$2000
TO…

## Slide 19: Time-Cost Relationship
Crashing costs increase as project duration decreases
Indirect costs increase as project duration increases
Reduce project length as long as crashing costs are less than indirect costs

## Slide 20: Time-Cost Tradeoff
Cost ($)
Project duration
Crashing Time
Minimum cost = optimal project time
Total project cost
Indirect cost
Direct cost

## Slide 21
Copyright 2011 John Wiley & Sons, Inc. All rights reserved. Reproduction or translation of this work beyond that permitted in section 117 of the 1976 United States Copyright Act without express permission of the copyright owner is unlawful. Request for further information should be addressed to the Permission Department, John Wiley & Sons, Inc. The purchaser may make back-up copies for his/her own use only and not for distribution or resale. The Publisher assumes no responsibility for errors, omissions, or damages caused by the use of these programs or from the use of the information herein.